## ProjectSchedule
CSE 543: GROUP 2-1
Arizona State University |  | Project Start: | 2022-09-01
Weekly Report 3 |  | Today: | 2022-10-30
|  | Display Week: | 1 |  |  | 2022-08-29 | [6 empty] | 2022-09-05 | [6 empty] | 2022-09-12 | [6 empty] | 2022-09-19 | [6 empty] | 2022-09-26 | [6 empty] | 2022-10-03 | [6 empty] | 2022-10-10 | [6 empty] | 2022-10-17
 | time axis 2022-08-29 to 2022-10-23
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2022-08-29 to 2022-10-23
Project Report annd Weekly Report Work: 1
Preparing Project Report | Amey Bhilegaonkar, Kasi Kishore Ravuri | 100% | 2022-09-01 | 2022-09-02 | 2
Motivation | Akash Roshan Mund | 30% | 2022-09-02 | 2022-09-05 | 4
Scope of Study | Bhavani Priya Kuche | 80% | 2022-09-03 | 2022-09-04 | 2
Expected Results | Rohit Vishwanath Badugu, Naveen Aaditya Chitirala | 60% | 2022-09-04 | 2022-09-05 | 2
References List | Everyone | 50% | 2022-09-05 | 2022-09-08 | 4
Final Project Proposal | Everyone | 100% | 2022-09-06 | 2022-09-08
Weekly Report Review | Everyone | 100% | 2022-09-07 | 2022-09-08 | 2
Project Report annd Weekly Report Work
Preparing Project Report | Rohit Vishwanath Badugu, Naveen Aaditya Chitirala | 100% | 2022-09-09 | 2022-09-11 | 3
Motivation | Akash Roshan Mund | 100% | 2022-09-10 | 2022-09-12 | 3
Scope of Study | Bhavani Priya Kuche | 100% | 2022-09-11 | 2022-09-13 | 3
Expected Results | Amey Bhilegaonkar, Kasi Kishore Ravuri | 100% | 2022-09-12 | 2022-09-14 | 3
References List | Everyone | 100% | 2022-09-13 | 2022-09-15 | 3
Final Project Proposal | Everyone | 100% | 2022-09-14 | 2022-09-16
Weekly Report Review | Everyone | 100% | 2022-09-15 | 2022-09-17 | 3
Reasearch Work
Use/Applications of ML in IAM Systems | TBD |  | 2022-09-01 | 2022-10-20 | 50
Use/Applications of Block Chain in IAM Systems | TBD |  | 2022-09-02 | 2022-10-20 | 49
Exploration of threats and attacks in IAM Systems | TBD |  | 2022-09-03 | 2022-10-20 | 48
Techniques to prevent different types of Attacks using M: | TBD |  | 2022-09-04 | 2022-10-20 | 47
Techniques to prevent different types of Attacks using BC | TBD |  | 2022-09-05 | 2022-10-20
Exploration of different measures, reasearch papers on topics related to IAM System in Cloud | TBD |  | 2022-09-06 | 2022-10-20
| TBD |  | 2022-09-07 | 2022-10-20
| TBD |  | 2022-09-08 | 2022-10-20 | 43
Adhoc Tasks
TBD | TBD |  | TBD | TBD | #VALUE!
TBD | TBD |  | TBD | TBD | #VALUE!
TBD | TBD |  | TBD | TBD | #VALUE!
TBD | TBD |  | TBD | TBD | #VALUE!
TBD | TBD |  | TBD | TBD | #VALUE!
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.